## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Work on Gender Impact assessments commenced late 2023 outside the current reporting period
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provide executive mentoring opportunities that are equally accessible for all staff in the organisation | Ongoing | In May 2022 VicTrack participated in the Women in Transport (WIT) Mentoring program. The program takes a strategic approach to empower women, with a view to shifting the dial in a sector typically dominated by men. Selected females participated it the Victorian Chamber of Commerce and Industry - Change Program Ascend In addition, in 2022 and 2023 VicTrack launched an internal Mentoring program – Mentorloop. The Mentorloop program was made available to all within the business to register their profiles in the system. Each registration allowed the individual to be a Mentor or Mentee or both, each participant completed a profile detailing their skills, knowledge and mentoring outcomes, the MentorLoop algorithm would then match individuals based on these profiles. | In 2022 seven individuals participated in the program, four as Mentees, three as Mentors. In 2023 three individuals participated, two as Mentees and one as a Mentor. The program closed in November 2023. Three senior females attended the Ascend Program Mentorloop (2022 program): 27 identified females (44%) (total enrolments 61) | This will be a year on year ongoing program | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Provide leadership development for women in senior positions, giving focus to those working in underrepresented areas. | In progress | Increased intersectional participation in leadership training | Gender balance is achieved with enrolment in leadership training and other development training Two female Executives have commenced MBA programs Cert IV in Leadership & Management: 4 identified females (40%) (total enrolments 10) Diploma of Leadership & Management: 9 identified females (60%) (total enrolments 15) Externally delivered programs female attendance: WLA Executive Ready - 2 Leading Edge - 1 | Ongoing YoY | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Develop a framework for succession planning and talent identification to support equitable career development. | Ongoing | During the reporting period VicTrack was awaiting the appointment of a permanent Chief Executive (CE). The position of Chief Executive and a number of Executive roles were being undertaken by individuals in an acting capacity, a decision was made to only conduct succession planning for Executive roles reporting into the CE and additionally in the parts of the Organisation where a permanent Executive was in place. In May 2023 succession planning activity was conducted for positions reporting into the CE, and for those directly reporting into a permanently appointed Executive position. As a part of the succession planning process, skill gaps and career development opportunities were identified. |  | Ongoing YoY | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Hold performance management discussions and make plans which include career development/ progression. Monitor the use of succession plans for gender balance | Ongoing | Individual Perfomance Management (IPM) plans are in place for all VicTrack employees and managed on a half yearly cycle. Employees and their Managers are responsible for drafting and approving their performance and career development plan. We plan to draw reports on IPMs based on gender demographics | Completion rate of IPMs in half yearly cycles Increase of Intersectional promotions internally Results from the 2022 People Matters Survey indicated. 62% of respondents ‘believe the recruitment process in my organisation is fair’ with 18% neither agreeing or disagreeing. 48% of respondents ‘I have an equal chance at promotion in my organisation’ with 32% neither agreeing or disagreeing. 42% of respondents ‘I believe the promotion processes in my organisation are fair’ with 34% neither agreeing or disagreeing. | Ongoing YoY | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Develop a proactive recruitment policy to ensure gender equality objectives are included and recruitment processes monitored, using data on applications received, shortlisting of candidates, and offers accepted by gender and classification levels. | In progress | Currently the Recruitment Policy and Procedure has limited information and guidance relating to gender equality. Recruitment Policy and Procedure documents are currently in review. | Shortlists to reflect a proportionate split of intersectional applicants where possible. Recruitment Policy and Procedure to be reviewed to include clearer guidelines and advice on gender equality hiring. Due to the nature of some specific specialist/technical roles, 50% gender balanced shortlists maybe difficult to achieve. | Planned for completion by March 2024 | Talent Acquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Analyse staff exit data to identify gender-related issues and take action to address appropriately. | In progress | Exit surveys and interviews have been conducted within the reporting period, it is noted that Intersectionality data was not being collected | A review of the exit survey is currently being conducted to ensure all appropritate intersectional data is collected to enable a review and identify actions. | 2024-02-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Hiring managers are trained in managing and reducing unconscious bias, resulting in greater diversity and more female hires, particularly in roles considered to be ‘male gendered’. | In progress | 6 sessions of unconcious bias training were delivered within the reporting period by Diversity Australia to 108 leaders, with 5 more sessions scheduled to be conducted by Oct 2023. Future sessions will be conducted year on year | At all times have at least one panel member who is trained in unconscious bias present in the interviews. | 2023-10-01 | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Gender equality principles are integrated into strategic workforce planning (talent attraction, development, and retention). | In progress | Introduction of an executive-approved Diversity and Inclusion Strategy and Policy |  | 2024-06-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Identify select positions that are male biased in composition and support them through flexible work arrangements. | In progress | Flexible work policy has been in place since 2021 that allows all staff to negotiate flexible work arrangements with their Managers. | Uptake of flexible work arrangements by male employees |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Explore the feasibility of reforming/extending our parental leave provisions (e.g., explore incentives for female staff to return to work sooner, encourage non-birth parents to take leave (that is referenced in the GEAP) and redefine primary/secondary caregiver application. | Complete | Current Parental leave provisions are detailed in VicTrack’s current Enterprise Agreement 2021 - 2025 This provision will be reviewed as part of the Enterprise Agreement negotiations commencing 2024 | Primary/Secondary caregiver was re-defined as part of EA 2021-25 and period extended to 16 weeks for primary, and 4 weeks for secondary. |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Ongoing review to ensure language and images in VicTrack’s recruitment documents and materials and communications are diverse and use inclusive language. | In progress | Images used on job advertising have been updated to be more gender inclusive. Language on all job advertising and Position Descriptions needs to be reviewed to ensure more inclusive language. | All Position Description and advertising templates re-coded with more inclusive language. | 2024-02-01 | Talent Acquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Use gender neutral job advertisements, interview invitations, specific recruitment and selection criteria and structured interviews. | Not started | Existing license to Broadbean recruitment SaaS includes access to their job advert language review feature for masculinity. However, due to technical/operational reasons, implementation of the product has been delayed. We are set to review and implement the feature by December 2023 | Increased number of female applicants | 2024-02-01 | Talent Acquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Continue to implement language that is gender neutral and inclusive (gender decoder) when writing/reviewing position descriptions and advertisements. | Not started | Existing license to Broadbean recruitment SaaS includes access to their job advert language review feature for masculinity. However, due to technical/operational reasons, implementation of the product has been delayed. We are set to review and implement the feature by December 2023 | Increased number of female applicants | 2024-02-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Review recruitment practice and content to ensure gender neutrality. | Not started | Existing license to Broadbean recruitment SaaS includes access to their job advert language review feature for masculinity. However, due to technical/operational reasons, implementation of the product has been delayed. We are set to review and implement the feature by December 2023 | Increased number of female applicants | 2024-02-01 | Talent Acquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
A select group of potential interview panel members to undergo online training or sit the Harvard Implicit Association Test. | In progress | Face-to-face Recruitment Excellence training will be conducted in conjunction with Diversity Australia in early 2024.This training is designed to further reduce unconscious bias during the hiring process. It will be delivered to all hiring managers and high performing females, with a view to increase female participation on recruitment panels. | At all times have at least one panel member (preferably female) who is trained in unconscious bias. | 2024-03-01 | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Pilot a select job and hide sex, gendered name, name of university or school, race, religion. | Not started |  |  | 2024-02-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
The EVP will include an aspect dedicated to increasing the diversity of women, with an emphasis on women with intersectional attributes that may result in underrepresentation in the business. | In progress | The Development of the EVP commenced mid 2023. This entailed the identification and engagement of an external provider to develop the EVP framework. |  | 2024-07-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Conduct facilitated training sessions for all employees on LGBTIQA+ awareness training. | Complete | All employees were invited to attend cultural awareness training sessions on LGBTIQA+ Safety in Tranport sessions to develop practical understanding of the challenges and barriers that affect LGBTIQA+ people. | People matter survey results have improved following the training sessions conducted resulting in greater understanding and awareness of the challenges this community faces along with encouraging a stronger sense of inclusiveness. |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Review the strategic workforce plan with a gender lens. Identify vacancies that can be offered to women only. | Not started |  |  |  | Talent Acquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Trial positions where women are underrepresented. | Not started |  |  |  | Talent Acquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Utilise social media channels to promote non-traditional female roles. | Not started |  |  |  | Comms and Engagement / Talent Acquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Continue to promote a zero tolerance for bullying, harassment and discrimination. | Ongoing | In November 2022 VicTrack implemented the Speak Up program. Speak Up provides a platform for individuals to raise concerns via multiple internal channels. Additionally, for those who do not feel comfortable using internal channels, we offer an anonymous Speak Up Integrity Hotline - an independent and externally managed service provided by third party vendor - Core Integrity. | Results from the 2022 People Matter Survey show a 2% (75% to 77%) increase in people feeling safe to speak up from the 2021 results. |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Further promote the consequences and effects of bullying and harassment. | Ongoing | Discrimination, harrassement and bulllying and their consequenses are included at Induction and repeated every two years via an e-learning compliance module. | Results from 2021 to 2022 People Matter Survey demonstrated a 2% decrease in Bullying & Harrassment. (8% to 6%) and sexual harrassment from 5% to 2%. In the years of 2021 and 2022 there were fewer than 5 complaints raised across the whole of VicTrack to People & Culture. |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Better communicate the importance of reporting sexual harassment, discrimination, and bullying. | Ongoing | The consequences of Discrimination, harrassement and bulllying are communicated at Induction and training is repeated every two years via an e-learning compliance module. | Results from the 2022 People matters survey show a 2% increase in people feeling safe to speak up from the 2021 results. In the 2022 People Matter Survey 12 people indicated they had experienced Bullying in the workplace., this is a decline of 2% from 2021 results. The report also highlighted fewer than 10 people said they had experienced Sexual Harassment, Discrimination, Violence or Aggression. These results are showing a percentage decline from 2021 results to 2022 results of: Sexual Harassment -3% Discrimination -1% and Violence or Aggression - 3% It is important to note that although these negative behaviours were highlighted within the survey, in 2021 78% and in 2022 100% stated they did not submit a formal complaint to People and Culture. |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
In collaboration with the LXRP Industry Capability & Inclusion, specialist employment services groups, Indigenous committees, and women’s groups, promote, train and support the business to better understand the impacts of intersectional attributes combined with gender. | In progress | Commenced participation in industry steering committee and focus groups: • Transport Portfolio Aboriginal self-determination steering committee. • Training for the future D&I Community of Practice • Women in Transport • BENT Transport / Pride Network for LGBTIQA+ | Greater year on year reporting on intesectionality measures. Increase and success in VicTrack employees participating in these groups and committees who are attending seminars, networking events, scholarships and woskhops. E.g. Public Sector Leadership Development Scholarship and Women and Leadership Australia Scholarship. |  | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Communicate and consult with people with physical disabilities, vision impairment, hearing impairment, intellectual disability, mental health issues, and people with communication or speech difficulties. | In progress | Mental health First Aiders are trained and available to all staff. Communication via the intranet informs staff who the Mental Health First Aiders are. Speaker event and increased communication on mental health issues on R U OK? Day conducted every year | Greater recruitment and retention of female employees with additional intersectional attributes, such as age, race, disability, gender. | 2024-07-01 | People and Culture
Continue with the current domestic violence support program, which includes trained domestic violence support officers and access to our Employee Assistance Program (EAP).Implement a support group if there is interest | Ongoing | EAP provider changed in 2023 to improve offerings and make it more accessible | 0 reported Domestic Violence Cases in the reporting period | 2024-07-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Ongoing promotion of flexible work arrangements, including hybrid home/office arrangements. | Complete | Continued implementation of VicTrack’s Flexible working policy and procedure. | 2022 People Matter Survey results show a percentage increase from the 2021 results of: How satisfied are you with the work life balance in your current job? + 9% I am confident that if I requested a flexible work arrangement, it would be given due consideration, + 6% |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Establish a keep-in-touch program for employees on carers leave and/or on-boarding support for workers returning from long-term leave | Ongoing | Our Enterprise agreement 2021 – 2025, Section 32 Parental Leave, aims to facilitate an easier return to employment at the end of the Parental Leave, during a period of Parental Leave, an Employee may attend and perform work for up to 10 days as paid Keeping in Touch Days, where VicTrack agrees to the Employee working that day. |  |  | People and Culture / Business Parters | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Conduct a deep dive analysis into the pay variances for same job types and levels between males and females. Remedy any differences | In progress | An initial analysis was conducted internally for all executive roles. This analysis highlighted some variances. Due to organisational changes, further action was put on hold until structures were confirmed. Organisational analysis across all levels commenced in late 2023 with a view to review data early 2024 | Future reports will show a decline and eventually more closley aligned pay across all Intersectionality. | 2024-07-01 | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
Examine commencing salaries by gender. | Not started | Organisational analysis across all levels of the Organisation commenced late 2023 with a view to review data early in 2024 | Future reports will show a decline and eventually an end to gender pay gaps. | 2024-05-01 | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
Increase representation of Aboriginal and Torres Strait Islander employees at VicTrack | Not started |  | Data has shown a decrease in representaion |  | Talent Aquisition | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Work with the LGBTQI+ focus group to raise cultural awareness and better promote VicTrack as an employer who supports the LGBTQI+ community. | In progress | All employees were invited to attend cultural awareness training sessions on LGBTIQA+ Safety in Tranport sessions to develop practical understanding of the challenges and barriers that affect LGBTIQA+ people. Lunch n Learn Q&A conducted LGBTIQA+ Commissioner's Senior Adviser attended as a guest speaker at VicTrack for an information session to discuss Pride in the Victorian Government and in the transport sector. | Success measures tie into row 27. These sessions were well represented across the broader VicTrack. In response to the to the Inclusion question within the 2022 People Matter Survey 83% of participants agreed ‘I can be myself at work’ with a further 15% neither agreeing or disagreeing, only 3% disagreed. |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Work with LGBTQI+ focus group and P&C to develop a gender affirmation policy. | In progress | A draft gender affirmation policy was drafted in Apri 2023. This was put on hold pending the recruitment of a new Organisational Development manager who commenced in July 2023. | Gender affirmation policy approved by Executive, published and communicated. In response to the to the Inclusion question within the 2022 People Matter Survey 83% of participants agreed ‘I can be myself at work’ with a further 15% neither agreeing or disagreeing, only 3% disagreed. | 2024-03-01 | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1: Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
The Executive General Manager, People and Culture was primarily accountable for the GEAP actions. However, due to an organisational restructure, this has been transferred to the Group Manager, People & Culture. Initially, the day-to-day responsibility for the implementation of GEAP sat with the Capability & Talent Manager, total allocation of resources equalled 1.7 FTE. On reviewing the progress of the GEAP, additional resources were approved for the project including: replacing the Capability & Talent Manager with an Organisational Development Manager with the support of 1.0 FTE as well as recruiting a Talent Acquisition Manager with the support of 1.0 additional FTE. Overall, we have nearly doubled the resourcing from 1.7 to 3.0 FTE. This includes support from business partnering and other functions within People & Culture. As this occurred in the latter part of 2023, the impact will not be seen until the future reporting period. We are currently recruiting a Senior Manager, Business Partnering to lead the business partnering team to support the roll out of several of the GEAP iniatives.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | No | Between 2021 and 2023, gender composition at VicTrack remained the same with 30% of the workforce identifying as female. However, there has been a marginal increase of 2% in the number of Female employees in full-time and ongoing roles. This trend is reversed in full-time fixed term roles with an increase in male representation by 4% and an equal decline in female employees within this cohort. This can be attributed to more female employees moving into ongoing roles. There has been a significant increase in male employees choosing to take up part-time permanent roles as a result of VicTrack's new Future Ways of Working strategy that strongly encourages a flexible and remote way of working. At the same time, there has been a marginal decrease in female employees in part-time ongoing employment. There has been no change in the gender composition in part-time fixed term employment type. VicTrack encourages hiring managers to recruit for longer term and more secure employment, in line with the principles of the Secure Jobs, Better Pay bill and as such, we have had only one male casual employee since 2021. | No | No | No | Yes | Yes | No | No | During the reporting period, VicTrack as a self funded agency was emerging from Covid and the effects of financial sustainability. This affected our ability to resource the initiatives.
Gender composition of governing bodies | Yes | In 2021, we had two male Board members and three female Board members. By 2023 we had an equal split in our Board as a result of a government initiative to have a balanced representation in Board members. It's important to note that the Minister for Public Transport appoints VicTrack's Board members. The Board chair identifies as a female and is included in the equal split. | No | No | No | No | No | No | No
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | No | When comparing the percentage difference of the average remuneration for women and service length a trend emerges showing that when there is an increase in service length there is also an increase in the percentage difference within some grades for women and remuneration. This is most visible in the Transition grade groups (This group was created under the 2015-19 Enterprise preserving existing salary entitlements which were incremental based. The longer the service the higher the remuneration. The majority of these employees were male). This trend validates employees who have been at VicTrack for longer periods benefiting from the compounding effects of annual remuneration increases through industrial mechanisms such as the enterprise agreement. In most cases staff that have less than two years’ service within the grades do not tend to have a difference in remuneration for women, with the exception of Job Family E (level -6), PROF job family. Furthermore, within the PROP and PROF job family women senior leaders (level -4) average remuneration is 8.35% and 6.82% less than the overall average for that group even though women’s average length of service is on par or above the average length for this group. Detailed report attached. In October 2023 we engaged the professional services of Diversity Australia to provide a more detailed Gender Pay Analysis. The data provided was at 1st October 2023, additional historical data has been provided as at 1st October for each respective year (2020,2021 and 2022) The analysis will be conducted in two distinct components; VicTrack Enterprise Agreement 2021-2025 and Executive roles. This approach reflects the significant differences in remuneration frameworks applicable to each of these cohorts. Demographic reporting will use the following demographic information. • Age • Gender • Length of tenure No intersectionality or analysis of the impacts of other demographics characteristics and dimensions of diversity are considered as these are not currently captured within our HRIS. The Analysis and reports will focus on several areas of significance, namely. • Gender • Job level and Band • Positional hierarchy (seniority) • Movement over the preceding three and two annual pay cycle periods Once the analysis is complete a detailed report including recommendations will be presented to the Executive. | No | Yes | No | No | No | No | No | Due to the size of VicTrack's workforce, the nature of work and aging infrastructure, traditional roles predominantly occupied by males were unable to be filled by females due to lack of experience (old infrastructure).
Sexual harassment in the workplace | Yes | Results from the 2022 People matters survey show a 2% increase in people feeling safe to speak up from the 2021 results. In the 2022 People Matter Survey 12 people indicated they had experienced Bullying in the workplace., this is a decline of 2% from 2021 results. The report also highlighted less than 10 people said they had experienced Sexual Harassment, Discrimination, Violence or Aggression. These results are showing a percentage decline from 2021 results to 2022 results of: Sexual Harassment -3% Discrimination -1% and Violence or Aggression - 3% It is important to note that although these negative behaviours were highlighted within the survey, in 2021 78% and in 2022 100% stated they did not submit a formal complaint to People and Culture. | No | No | No | No | No | No | Yes | VicTrack's Executive and Senior Leadership team have made a concerted effort in improving the awareness of harassment in the workplace. This is evidenced by our results.
Recruitment and promotion practices in the workplace | No | Recruitment Since 2021, VicTrack has significantly increased it's overall headcount, thereby resulting in a higher number of new recruits. However, the gender ratio has remained largely the same with 69% of new recruits in 2021 identifying as male, compared to 66% in 2023. While this ratio has remained the same, it's important to note that we recruited 66 female employees in 2023 compared to just 19 in 2021. In 2021, of all the 19 women we recruited, 9 (~47%) were in between 35-44 years of age. The percentage of total women recruited in 2023 in the 35-44 years age group remained similar with 33 of 66 (~45%) being female employees. We also increased the number of female employees in the 15-24 age group by 2, giving opportunities to women early on in their career. Throughout the reporting period from 2021, no female employees over the age of 65 were recruited. We did recruit 3 male employees over 65 years of age in 2023 compared to just 1 in 2021. However, in 2023 we recruited 6 female employees in the 55-64 year age group in senior roles, which increased from 2 employees in 2021. The number of male employees recruited in this age group also increased from 12 to 23 in 2023. This increase is due to our overall headcount increase and the need for signficant experience in complex project delivery roles. Promotions and secondments Our 2021 audit showed that 35% of all promotions were awarded to women across all levels of the organisation. While the number of women who received a promotion in the 2023 audit increased, it remained similar to the 2021 ratio at 34%. In 2021, 23 men acted in higher duties along with 13 women, most of them in lower and middle levels, allowing for career development. The overall number of employees acting in higher duties reduced to 21 in the 2023 audit. One of the causes can be attributed to an increase in secondment opportunities from 15 employees to 39 in 2023. The gender split for secondments remained largely the same, indicating that gender had no effect in awarding secondments. People Matter Survey results In the 2021 results, 37% of respondents agreed that they had an equal chance at promotion, this increased significantly in the 2023 survey with 53% of respondents agreeing.as a result of an emphasis on transparency in the application process and improving access to promotion opportunities across the organisation. We experienced a similar and healthy increase in the number of respondents agreeing that promotion decisions are fair and based on merit. It increased from 55% to 62% of respondents. | No | No | No | Yes | Yes | No | No | During the reporting period, VicTrack as a self funded agency was emerging from Covid and the effects of financial sustainability. This affected our ability to resource the initiatives.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Flexible working arrangements In 2021, 26 Males and 18 Females entered into a formal flexible work agreement, The introduction in Dec 2021 of the Flexible Work Policy, as part of VicTrack’s Future Ways of Working strategy, all roles are considered flexible and hybrid by default. This means that we start from a position of flexibility and assess the requirements of the role together with employee preferences to determine options for flexibility in working times and location. In the reporting period flexible working arrangements were: Working remotely 507 Purchased leave 29 Working more hours over fewer days 2 Working part-time 28 | No | No | No | No | No | No | Yes | VicTrack's Future Way of Work Strategy was adapted by the VPSC and promoted as a model framework for other public service and sector agencies. This included flexible work arrangements .
Gendered segregation within the workplace | Yes | Results from the 2022 People matters survey show a 2% increase in people feeling safe to speak up from the 2021 results. In the 2022 PMS 78% of staff who did the survey responded positively to questions about Inclusion, this was not asked in the 2021 survey Data comparisons in People matter survey from 2021 to 2022 : ‘People in my workgroup treat each other with respect’ 2021 @ 93% - 2022 @ 92% ‘My manager treats employees with dignity and respect’ 2021 @ 90% - 2022 @ 89% ‘I understand how the Charter of Human Rights and Responsibilities applies to my work’ 2021 @ 62% - 2022 @ 67% In 2021 86% indicated ‘My organisation encourages respectful workplace behaviours’ in 2022 response was at 84% In 2021 86% indicated ‘I feel culturally safe at work’ 2022 response was at 84% 2022 PMS 70% agreed ‘My organisation takes steps to eliminate bullying, harassment and discrimination’ with 22 % neither agreeing or disagreeing compared to 73% and 16% respectively in 2021 Pulse Survey In VicTrack's half yearly pulse survey, we have consistently scored high 70s for Engagement in the previous three surveys. We have also maintained a low mental health score of 2.4%. | No | No | No | No | No | No | Yes | VicTrack's Executive and Senior Leadership team have made a concerted effort in improving the awareness of inclusion in the workplace. In addition to this, VicTrack also implemented an anonymous Speak Up hotline.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled